NitNab

Liquid Glass Implementation Plan

Direction 05 — Contextual Tint System with Liquid Glass Material

Prepared by Deloitte Digital

Under Apple Design Leadership

February 26, 2026

macOS Tahoe 26  ·  Apple Intelligence  ·  100% On-Device

# Executive Summary

This document outlines the full implementation plan for applying the Liquid Glass brand direction (Direction 05) to NitNab, a privacy-first, on-device transcription app for macOS Tahoe 26+. The plan covers design token creation, view-by-view implementation, testing strategy, timeline, and risk management.

The Liquid Glass direction uses macOS Tahoe’s translucent material system with a contextual tint approach. Each functional area of the app receives its own Apple system color identity: Transcript (.blue), Summary (.indigo), Chat (.purple), Privacy (.green), and Audio (.orange). All implementation uses pure Apple platform APIs with zero custom colors, zero custom fonts, and zero asset catalogs.

# Phase 1: Foundation (Week 1–2)

## 1.1 Design Token Layer

- Create NitNabTokens.swift with spacing (4pt–64pt), radius (8pt–980pt), and tint enums

- Define NitNabContext enum mapping tabs to Apple system colors

- Create GlassModifier ViewModifier wrapping .glassEffect(in: .rect(cornerRadius: 16))

- Establish NitNabTint environment key for contextual tinting across the view hierarchy

## 1.2 App Shell Updates

- Update NitNabApp.swift to inject contextual tint environment at WindowGroup level

- Apply .glassEffect() to main window container

- Configure sidebar width to 240pt default per HIG

## 1.3 Typography Audit

- Audit all 12 view files for hardcoded font sizes and replace with Dynamic Type tokens

- Verify all text supports Dynamic Type accessibility scaling at all 7 size categories

# Phase 2: Core Views (Week 3–4)

## 2.1 ContentView + Tab Switching

- Apply glass material to main container and implement tab-aware contextual tint switching

- Replace Color(nsColor: .controlBackgroundColor) with system semantic colors throughout

- Add .clipShape(.rect(cornerRadius: 16, style: .continuous)) to all panels

## 2.2 StandardView + AdvancedView

Apply contextual tints per functional area: .blue (transcript), .indigo (summary), .purple (chat), .green (privacy), .orange (audio). Add glass material to all card containers.

## 2.3 DropZoneView, TranscriptView, FileListView

Redesign with glass material, animate tint on file hover (.orange for audio context), apply 16pt continuous corners, glass inner surfaces for accepted files, blue tint context on transcript, 12pt continuous corners on file list rows.

# Phase 3: Supporting Views (Week 5–6)

- HeaderView: Glass toolbar background, contextual tint for active tab, 52pt toolbar height, pill controls

- SettingsView + MemoriesSettingsView: Standard grouped list styling, 20pt card padding

- TagCloudView + CompanyPickerSheet: Pill tags (8pt), glass sheet (22pt continuous corners)

- SearchBarView: Glass background, 8pt spacing grid compliance

# Phase 4: Polish & QA (Week 7–8)

- Light/Dark appearance audit: Verify all glass materials in both modes, validate WCAG AA contrast ratios

- Dynamic Type testing: All 11 text styles at all sizes, layout integrity at largest sizes

- Animation: Smooth tint transitions between tabs, glass material fade-in, Reduce Motion compliance

- Performance: Profile .glassEffect() GPU impact, backdrop blur at 40pt, minimum-spec hardware testing

- Screenshot-based visual regression testing against brand kit PDF

# Risk Register

| Risk | Likelihood | Impact | Mitigation |
| --- | --- | --- | --- |
| .glassEffect() performance on older Apple Silicon | Medium | High | Profile early in Phase 1; provide opaque fallback path |
| Liquid Glass API changes in Tahoe beta | Low | High | Pin to stable API surface; monitor WWDC sessions |
| Dynamic Type breaks glass layouts | Medium | Medium | Test all 7 size categories in Phase 4 |
| Contrast ratio failures on glass | Medium | High | Pre-validate all tint/glass combinations against WCAG AA |
| Scope creep from Apple Design review | High | Medium | Phase-gate deliverables; weekly sign-off |

# Team & Governance

## Deloitte Digital

- Engagement Lead — Client relationship, Apple Design liaison

- Design Lead — Brand kit fidelity, HIG compliance review

- SwiftUI Engineers (2) — Implementation, token system, glass materials

- QA Lead — Accessibility, performance, visual regression testing

- Project Manager — Timeline, risk management, sprint planning

## Apple Counterparts

- Lead Designer — Creative direction, approval authority

- SwiftUI Framework Engineer — .glassEffect() technical guidance

- HIG Review — Compliance sign-off at phase gates

— End of Document —