## Project Timeline
NitNab — Liquid Glass Implementation Timeline
Deloitte Digital · Under Apple Design Direction · February 2026
Phase | Task ID | Task | Owner | Start | End | Duration | Status
Phase 1: Foundation | 1.1 | Create NitNabTokens.swift design token layer | SwiftUI Engineer 1 | Wk 1 Mon | Wk 1 Wed | 3 days | Not Started
| 1.2 | Define NitNabContext enum + GlassModifier | SwiftUI Engineer 1 | Wk 1 Thu | Wk 1 Fri | 2 days | Not Started
| 1.3 | Update NitNabApp.swift shell (glass, tint env) | SwiftUI Engineer 2 | Wk 1 Mon | Wk 1 Thu | 4 days | Not Started
| 1.4 | Typography audit (all 12 view files) | Design Lead | Wk 2 Mon | Wk 2 Wed | 3 days | Not Started
| 1.5 | Dynamic Type compliance pass | SwiftUI Engineer 2 | Wk 2 Thu | Wk 2 Fri | 2 days | Not Started
| 1.6 | Phase 1 Apple Design review | Engagement Lead | Wk 2 Fri | Wk 2 Fri | 0.5 days | Not Started
Phase 2: Core Views | 2.1 | ContentView + tab-aware tint switching | SwiftUI Engineer 1 | Wk 3 Mon | Wk 3 Wed | 3 days | Not Started
| 2.2 | StandardView glass + contextual tints | SwiftUI Engineer 1 | Wk 3 Thu | Wk 3 Fri | 2 days | Not Started
| 2.3 | AdvancedView glass + contextual tints | SwiftUI Engineer 2 | Wk 3 Mon | Wk 3 Wed | 3 days | Not Started
| 2.4 | DropZoneView redesign (glass, orange tint) | SwiftUI Engineer 2 | Wk 3 Thu | Wk 4 Mon | 2 days | Not Started
| 2.5 | TranscriptView (blue tint, glass container) | SwiftUI Engineer 1 | Wk 4 Mon | Wk 4 Tue | 2 days | Not Started
| 2.6 | FileListView + SearchBarView glass rows | SwiftUI Engineer 2 | Wk 4 Tue | Wk 4 Thu | 3 days | Not Started
| 2.7 | Phase 2 Apple Design review | Engagement Lead | Wk 4 Fri | Wk 4 Fri | 0.5 days | Not Started
Phase 3: Supporting | 3.1 | HeaderView glass toolbar + tab indicator | SwiftUI Engineer 1 | Wk 5 Mon | Wk 5 Tue | 2 days | Not Started
| 3.2 | SettingsView + MemoriesSettingsView grouped styling | SwiftUI Engineer 2 | Wk 5 Mon | Wk 5 Wed | 3 days | Not Started
| 3.3 | TagCloudView pills + CompanyPickerSheet glass | SwiftUI Engineer 1 | Wk 5 Wed | Wk 5 Thu | 2 days | Not Started
| 3.4 | SearchBarView glass styling | SwiftUI Engineer 2 | Wk 5 Thu | Wk 5 Fri | 1 day | Not Started
| 3.5 | 8pt grid spacing audit (all views) | Design Lead | Wk 6 Mon | Wk 6 Wed | 3 days | Not Started
| 3.6 | Phase 3 Apple Design review | Engagement Lead | Wk 6 Fri | Wk 6 Fri | 0.5 days | Not Started
Phase 4: Polish & QA | 4.1 | Light/Dark appearance full audit | QA Lead | Wk 7 Mon | Wk 7 Wed | 3 days | Not Started
| 4.2 | Dynamic Type testing (all 7 size categories) | QA Lead | Wk 7 Thu | Wk 7 Fri | 2 days | Not Started
| 4.3 | Animation polish + Reduce Motion compliance | SwiftUI Engineer 1 | Wk 7 Mon | Wk 7 Wed | 3 days | Not Started
| 4.4 | Performance profiling (.glassEffect() GPU) | SwiftUI Engineer 2 | Wk 7 Thu | Wk 8 Mon | 2 days | Not Started
| 4.5 | WCAG AA contrast ratio validation | Design Lead | Wk 8 Mon | Wk 8 Tue | 2 days | Not Started
| 4.6 | Screenshot regression vs brand kit PDF | QA Lead | Wk 8 Wed | Wk 8 Thu | 2 days | Not Started
| 4.7 | Final Apple Design review + sign-off | Engagement Lead | Wk 8 Fri | Wk 8 Fri | 1 day | Not Started

## Design Tokens
NitNab — Liquid Glass Design Token Reference
Contextual Tint System
Context | Light Hex | Dark Hex | SwiftUI | Used In
Transcript | #007AFF | #0A84FF | .tint(.blue) | Transcript tab, text view, word count
Summary | #5856D6 | #5E5CE6 | .tint(.indigo) | AI summary, key points, action items
Chat | #AF52DE | #BF5AF2 | .tint(.purple) | Chat interface, AI responses, prompts
Privacy | #34C759 | #30D158 | .tint(.green) | On-device badge, privacy checkmarks
Audio | #FF9500 | #FF9F0A | .tint(.orange) | Waveform, playback, recording status
Glass Material Tokens
Property | Light Value | Dark Value | SwiftUI Implementation
Background | rgba(255,255,255,0.72) | rgba(28,28,30,0.65) | .glassEffect(in: .rect(cornerRadius: 16))
Border | rgba(255,255,255,0.40) | rgba(255,255,255,0.06) | Automatic with .glassEffect()
Backdrop Blur | 40pt | 40pt | Built into .glassEffect()
Secondary Glass | rgba(255,255,255,0.50) | rgba(28,28,30,0.45) | .glassEffect() with nested views
Secondary Blur | 20pt | 20pt | Automatic layering
Spacing Grid (Apple 8pt)
Token | Value | Usage | SwiftUI
space.2xs | 4pt | Icon-to-label inline gap | .padding(4)
space.xs | 8pt | Chip internal, tight groupings | .padding(8)
space.sm | 12pt | Related element pairs | .padding(12)
space.md | 16pt | Standard content padding | .padding()
space.lg | 20pt | Card internal, form fields | .padding(20)
space.xl | 24pt | Section separation | .padding(24)
space.2xl | 32pt | Group separation | .padding(32)
space.3xl | 40pt | Major layout divisions | .padding(40)
space.4xl | 64pt | Hero/header regions | .padding(64)
Corner Radius (Continuous/Superellipse)
Token | Value | Usage | SwiftUI
radius.sm | 8pt | Buttons, chips, small controls | .clipShape(.rect(cornerRadius: 8, style: .continuous))
radius.md | 12pt | Cards, list rows | .clipShape(.rect(cornerRadius: 12, style: .continuous))
radius.lg | 16pt | Panels, grouped containers | .clipShape(.rect(cornerRadius: 16, style: .continuous))
radius.xl | 22pt | Modals, sheets | .clipShape(.rect(cornerRadius: 22, style: .continuous))
radius.pill | 980pt | Pills, full-round buttons | .clipShape(Capsule())

## File Inventory
NitNab — Source File Inventory & Implementation Status
Category | File | Changes Required | Priority | Phase | Status
App Entry | NitNabApp.swift | Glass window, tint env injection | P0 | Phase 1 | Not Started
View | ContentView.swift | Glass material, tab tint switching | P0 | Phase 2 | Not Started
View | StandardView.swift | Glass cards, contextual tints | P0 | Phase 2 | Not Started
View | AdvancedView.swift | Glass cards, contextual tints | P0 | Phase 2 | Not Started
View | DropZoneView.swift | Glass redesign, orange tint hover | P1 | Phase 2 | Not Started
View | TranscriptView.swift | Blue tint, glass container | P0 | Phase 2 | Not Started
View | FileListView.swift | Glass rows, 12pt continuous corners | P1 | Phase 2 | Not Started
View | SearchBarView.swift | Glass background, grid spacing | P1 | Phase 2 | Not Started
View | HeaderView.swift | Glass toolbar, tab tint indicator | P1 | Phase 3 | Not Started
View | SettingsView.swift | Grouped list styling, 20pt padding | P2 | Phase 3 | Not Started
View | MemoriesSettingsView.swift | Grouped list styling | P2 | Phase 3 | Not Started
View | TagCloudView.swift | Pill tags (8pt corners) | P2 | Phase 3 | Not Started
View | CompanyPickerSheet.swift | Glass sheet, 22pt modal corners | P2 | Phase 3 | Not Started
New File | NitNabTokens.swift | Spacing, radius, tint enums | P0 | Phase 1 | Not Started
New File | GlassModifier.swift | .glassEffect() ViewModifier | P0 | Phase 1 | Not Started
ViewModel | TranscriptionViewModel.swift | Tint context state management | P1 | Phase 2 | Not Started
Service | AIService.swift | No visual changes | P3 | N/A | No Changes
Service | TranscriptionService.swift | No visual changes | P3 | N/A | No Changes
Service | DatabaseService.swift | No visual changes | P3 | N/A | No Changes
Service | ExportService.swift | No visual changes | P3 | N/A | No Changes
Model | AudioFile.swift | No changes | P3 | N/A | No Changes
Model | TranscriptionJob.swift | No changes | P3 | N/A | No Changes
Model | TranscriptionResult.swift | No changes | P3 | N/A | No Changes